## Overview
PUCSL Submission — Master Response Workbook
Assignment | Assessment on Cybersecurity Readiness of Electricity Network and Critical Generation Facilities in Sri Lanka and Development of a Cybersecurity Audit Framework Specific to Grid Operations, SCADA and Critical Infrastructure Protection
Client / Procuring Entity | Public Utilities Commission of Sri Lanka (PUCSL)
Bidding Structure | Joint Venture: Platinum High Integrity Technologies Limited (Malta) — Lead JV Partner; EML Consultants PLC (Sri Lanka) — Local JV Partner (agreed by email 27–28 Jul 2026)
Technical Lead | Abatis Security Innovations & Technologies GmbH (Switzerland) — product, methodology, specialist cybersecurity scope
Commercial Allocation | ~70% Platinum/Abatis, ~30% EML (working basis; EML local component to remain below 40%, expected ≈30%)
Submission | EML coordinates physical preparation and submission in Sri Lanka; all final documentation approved by both parties before submission
Evaluation | 80% Technical / 20% Financial (per EML briefing, 27 Jul 2026 call)
Deadline | Thursday 30 July 2026 (per EML: 3 days from 27 Jul call) — CONFIRM exact time & venue with EML
Core Frameworks | C2M2 (DOE Cybersecurity Capability Maturity Model), IEC 62443, NIST Cybersecurity Framework, ISO/IEC 27001/27019; NERC CIP as reference good practice
Status Date | 29 July 2026
How to use this workbook
1. 'Submission Checklist' — every document the JV must produce, with status and owner.
2. 'Technical Response Matrix' — TOR requirement areas with drafted responses (Abatis sections complete; verify against the official tender document once purchased).
3. 'Approach & Methodology' and 'Work Plan' — the phased delivery model matching the budget.
4. 'Staffing & Rates' and 'Financial Summary' — mirror of Budget_cyber_security.xlsx.
5. 'Key Personnel' — nominated experts and credentials.
6. 'Q&A Answers' — answers to standard tender questions we can already answer.
7. 'Outstanding Items' — what is still needed, from whom, to complete the submission.

## Submission Checklist
No. | Document / Form | Owner | Status | Notes / Evidence
A | TECHNICAL PROPOSAL
1 | Technical Proposal Submission Form / Covering Letter (signed by Lead JV Partner + EML) | Platinum + EML | DRAFT NEEDED | Letter text drafted in PUCSL_Technical_Proposal_Draft.md §1; needs letterhead + signatures
2 | Consultant's Organisation & Experience (firm profiles, similar assignments) | Both | IN PROGRESS | EML profile received (uploaded). Abatis/Platinum profile & reference assignments to be inserted — see Q&A sheet rows 5–9
3 | Comments / Suggestions on the Terms of Reference | Abatis | DRAFTED | See Technical Response Matrix rows 20–23; finalise against official TOR
4 | Description of Approach, Methodology & Work Plan | Abatis | DRAFTED | See Approach & Methodology + Work Plan sheets; narrative in proposal draft §3–4
5 | Team Composition & Task Assignments | Both | DRAFTED | Key Personnel sheet; EML to confirm SCADA/Electrical engineer nominee
6 | CVs of Key Experts (signed) | Both | OUTSTANDING | Abatis: Glyn Richards, Debbie Richards, Chris Barter, Christian Rogan (+ Alex Shipp / William if academic credentials required). EML: DPM SCADA engineer, electrical engineer, stakeholder specialist
7 | Work Schedule / Staffing Schedule (bar chart) | Abatis | DRAFTED | Work Plan sheet; convert to required form format
B | FINANCIAL PROPOSAL
8 | Financial Proposal Submission Form | EML | OUTSTANDING | Totals from Financial Summary sheet: USD 192,790.63 excl. taxes; USD 233,180.26 incl. VAT 18% + SSCL 2.5%
9 | Summary of Costs / Breakdown by activity | EML + Abatis | DONE (internal) | Budget_cyber_security.xlsx mirrored in Financial Summary sheet
10 | Breakdown of Remuneration (rates × man-days) | EML + Abatis | DONE (internal) | Staffing & Rates sheet
11 | Reimbursable Expenses breakdown | EML | DONE (internal) | Travel, workshops, admin lines in Financial Summary
C | JOINT VENTURE / LEGAL
12 | Letter of Intent to form JV (both parties, signed) | Platinum + EML | IN PROGRESS | JV terms agreed by email 27–28 Jul; Platinum Malta = Lead. EML preparing JV intent letter
13 | Power of Attorney / authorisation of signatory | Both | OUTSTANDING | Confirm PUCSL requirement in official tender doc
14 | Bid Security / Bid Declaration (if required) | EML | UNKNOWN | Ask EML — not visible in draft RFP discussion
D | EML STATUTORY DOCUMENTS (received 29 Jul 2026)
15 | Business Registration — EML Consultants PLC | EML | RECEIVED | Reg. No. PQ 00240481 (ROC + Colombo Stock Exchange); name change from (Pvt) Ltd effective 19 Nov 2021 — BR_of_EML.pdf
16 | Company Profile | EML | RECEIVED | EML_COMPANY_PROFILE.pdf — est. 1993 (with E&Y and DHV Netherlands), fully Sri Lankan-owned 2003, listed CSE 2022; only listed consultancy on CSE; 600+ projects
17 | Audited Financial Statements — last 3 years | EML | RECEIVED | EML_Financial_Statements_for_last_3_years.pdf (scanned) — auditor: Lakshman Rupasinghe & Co.
18 | ISO Certifications | EML | RECEIVED | ISO 9001:2015 Cert GISL-0009-QC and ISO 14001:2015 Cert GISL-0009-EC; both initial date 06 Feb 2026 window 2025.02.06–2028.02.05 (verify dates on certificate)
E | PLATINUM / ABATIS CORPORATE DOCUMENTS
19 | Certificate of Incorporation — Platinum High Integrity Technologies (Malta) | Platinum | OUTSTANDING | Lead JV partner entity; required to mirror EML statutory set
20 | Certificate of Incorporation — Abatis Security Innovations & Technologies GmbH (CH) | Abatis | OUTSTANDING | Swiss registry extract; incorporated Oct 2004
21 | Abatis/Platinum company profile & credentials pack | Abatis | OUTSTANDING | 20+ yrs CNI protection; first client Swiss government/military; zero reported breaches, zero CVEs; deployments incl. Gulf smart-city OT programmes
22 | Platinum/Abatis financial statements (if required of both JV partners) | Platinum | UNKNOWN | Confirm whether PUCSL requires financials from both JV partners
23 | Professional memberships evidence (MCIIS, IISP) | Abatis | OUTSTANDING | Chris Barter — Full Member, Chartered Institute of Information Security (MCIIS); Glyn & Debbie Richards — full members IISP

## Technical Response Matrix
Ref | TOR Requirement / Theme | Our Response (summary) | Lead | Where Detailed
1 | SCOPE — READINESS ASSESSMENT
1.1 | Assess cybersecurity readiness of the electricity transmission & distribution network and critical generation facilities | Structured assessment across governance, architecture, OT/ICS operations: document review → site visits → structured interviews (multiple seniority levels per role) → control validation. Coverage: system control centre(s), SCADA/EMS masters, substations/RTUs, generation plant DCS, telecoms/WAN, IT/OT boundary. | Abatis | Proposal §3.1; Approach rows 3–8
1.2 | Evaluate security maturity of SCADA and Energy Management Systems using C2M2 | DOE C2M2 v2.1 self-evaluation facilitated and independently scored by Abatis across all 10 domains (ASSET, THREAT, RISK, ACCESS, SITUATION, RESPONSE, THIRD-PARTIES, WORKFORCE, ARCHITECTURE, PROGRAM); MIL0–MIL3 scoring per objective, evidence-based, with target-profile gap analysis. | Abatis | Proposal §3.2
1.3 | Identify threats, vulnerabilities and risks to grid operations | Threat modelling aligned to MITRE ATT&CK for ICS; utility-specific threat scenarios (ransomware on EMS, supply-chain compromise, remote-access abuse, insider, nation-state pre-positioning); risk register with likelihood × impact on safety/reliability/compliance; prioritised treatment plan. | Abatis | Proposal §3.3
1.4 | Benchmark against international standards & good practice | Gap analysis vs IEC 62443 (zones/conduits, SL-T vs SL-A), NIST CSF 2.0, ISO/IEC 27001/27019, with NERC CIP used as reference model for CIP obligations. | Abatis | Proposal §3.4
2 | SCOPE — AUDIT FRAMEWORK DEVELOPMENT
2.1 | Develop a Cybersecurity Audit Framework specific to grid operations, SCADA and critical infrastructure protection | Tailored PUCSL audit framework: audit universe & scoping model; control catalogue mapped to C2M2/IEC 62443/NIST CSF; audit procedures & evidence requirements per control; maturity-based scoring & reporting templates; audit frequency & regulatory escalation model; auditor competency requirements. | Abatis | Proposal §4
2.2 | Regulatory guidance & local SOPs | SOPs and regulatory guidance notes localised for Sri Lankan utilities co-developed with EML; alignment with existing PUCSL regulatory instruments and pending national cyber legislation gaps. | EML + Abatis | Proposal §4.3
3 | SCOPE — CAPACITY BUILDING
3.1 | Institutional capacity building & workshops | 4 workshops: Kick-off; Technical Findings & Governance Framework; Knowledge Transfer; Executive Presentation & Final. Training materials provided; local delivery logistics by EML. | EML lead, Abatis content | Work Plan; Financial Summary section D
3.2 | Knowledge transfer to PUCSL / utility staff | Auditor enablement: train PUCSL team on operating the audit framework, C2M2 re-assessment, and continuous monitoring; handover pack incl. templates and scoring tools. | Abatis | Proposal §5
4 | DELIVERABLES
4.1 | Inception Report | Mobilisation, confirmed methodology, stakeholder map, data request register, detailed schedule — end Phase 1. | Abatis | Work Plan
4.2 | Cybersecurity Readiness Assessment Report | Current-state assessment, C2M2 maturity scores per domain, threat & risk assessment, prioritised remediation roadmap. | Abatis | Work Plan
4.3 | Cybersecurity Audit Framework (for PUCSL adoption) | Framework document + control catalogue + audit procedures + reporting templates + implementation guidance. | Abatis | Work Plan
4.4 | Training & capacity building materials; workshop reports | Materials for all 4 workshops; attendance & outcome reports. | EML + Abatis | Work Plan
4.5 | Final Report & Executive Presentation | Consolidated findings, roadmap, audit framework adoption plan; executive briefing to PUCSL leadership. | Abatis | Work Plan
5 | COMMENTS ON TOR (TECH-3)
5.1 | Secure document exchange | Recommend a secured artefact-collection portal for assessment evidence (no such portal currently exists at PUCSL/EML); Abatis to provide secure exchange arrangement for the engagement. | Abatis | Proposal §6
5.2 | Scope clarity on facilities count | Request confirmation of number of generation facilities/substations in scope to firm up site-visit programme (budget assumes 2 international missions, 20 site-days). | Abatis | Outstanding Items
5.3 | Academic credential emphasis | TOR appears to weight academic qualifications heavily. JV approach: EML fields degree-qualified engineering staff; Abatis fields senior practitioners with professional certifications (MCIIS, IISP) plus academically credentialed specialists where required. | Both | Key Personnel
5.4 | Legislative context | National cyber legislation is nascent/outdated; framework will be designed to operate under current law while being forward-compatible with anticipated CNI legislation — and JV can support subsequent legislative drafting as follow-on advisory. | Abatis | Proposal §7

## Approach & Methodology
Phase | Activities | Method / Standards | Outputs | Indicative Timing
Phase 0 — Mobilisation & Inception | Kick-off workshop; confirm scope, stakeholder map, data request register; NDAs & secure exchange; logistics | PMI-aligned PMO by EML DPM; Abatis Team Leader directs technical scope | Inception Report; Kick-off Workshop | Weeks 1–2
Phase 1 — Information Gathering | Collect policies, procedures, network/SCADA architecture, asset registers, incident history; desk review; gap log | Doc review against C2M2/IEC 62443/NIST CSF control expectations | Document review register; preliminary gap log | Weeks 2–4
Phase 2 — Interviews & Site Assessment | Structured interviews across roles & seniority levels (operators to executives); site visits to control centres, substations, generation plants; control validation | Interview protocol testing whether processes are understood and actually followed; field validation by EML SCADA/electrical engineers with Abatis OT specialists | Interview records; site assessment notes; validated control evidence | Weeks 4–8
Phase 3 — Maturity & Risk Analysis | C2M2 scoring (10 domains, MIL0–3); threat modelling (MITRE ATT&CK for ICS); vulnerability & risk assessment; benchmark vs IEC 62443 / NIST CSF / ISO 27019 | Evidence-based scoring, moderated scoring workshop; risk register with treatment options | Readiness Assessment Report (draft); C2M2 maturity profile; risk register & roadmap | Weeks 8–11
Phase 4 — Audit Framework Development | Design PUCSL-specific audit framework: audit universe, control catalogue, procedures, scoring & reporting templates, audit cycle, auditor competencies; localise SOPs & regulatory guidance | Mapped to C2M2 / IEC 62443 / NIST CSF; consistent with PUCSL regulatory mandate | Cybersecurity Audit Framework (draft); SOPs; regulatory guidance notes | Weeks 10–13
Phase 5 — Validation & Capacity Building | Technical Findings & Governance Framework workshop; incorporate feedback; Knowledge Transfer workshop (auditor enablement); finalise deliverables | Workshop-driven validation; train-the-trainer materials | Final Readiness Report; Final Audit Framework; training materials & workshop reports | Weeks 13–15
Phase 6 — Close-out | Executive Presentation & Final Workshop; final report acceptance; handover pack; follow-on roadmap discussion | Executive briefing to PUCSL leadership | Final Report; Executive Presentation; handover pack | Week 16

## Work Plan (16 wks)
Activity | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Mobilisation & Inception | █ | █
Kick-off Workshop |  | █
Information Gathering |  | █ | █ | █
Interviews (multi-level) |  |  |  | █ | █ | █ | █
Site Visits & Field Assessment |  |  |  |  | █ | █ | █ | █
C2M2 Maturity Scoring | [7 empty] | █ | █ | █
Threat & Risk Assessment | [7 empty] | █ | █ | █ | █
Standards Benchmark (IEC 62443/NIST) | [8 empty] | █ | █ | █
Draft Readiness Assessment Report | [9 empty] | █ | █ | █
Audit Framework Development | [9 empty] | █ | █ | █ | █
SOPs & Regulatory Guidance (EML+Abatis) | [10 empty] | █ | █ | █
Technical Findings Workshop | [11 empty] | █
Knowledge Transfer Workshop | [13 empty] | █
Finalise Deliverables | [12 empty] | █ | █ | █
Executive Presentation & Final Workshop | [15 empty] | █

## Staffing & Rates
No. | Role | Party | Unit | Rate (USD) | Qty | Amount (USD)
1 | Team Leader | Abatis | Man-Day | 750 | 30 | 22500
2 | Senior OT/ICS Cybersecurity Specialist | Abatis | Man-Day | 720 | 60 | 43200
3 | Cybersecurity Governance Specialist | Abatis | Man-Day | 620 | 20 | 12400
4 | IEC 62443 / C2M2 Specialist | Abatis | Man-Day | 650 | 5 | 3250
5 | Training & Capacity Building Specialist | Abatis | Man-Day | 550 | 5 | 2750
8 | Technical Proposal Development | Abatis | Lump Sum |  |  | 5000
9 | Power Systems / SCADA Engineer (DPM) | EML | Man-Day | 190 | 50 | 9500
10 | Local Electrical Engineer | EML | Man-Day | 155 | 25 | 3875
11 | Stakeholder Engagement Specialist | EML | Man-Day | 140 | 15 | 2100
12 | QA/QC Manager | EML | Man-Day | 180 | 10 | 1800
13 | Technical Report Coordinator | EML | Man-Day | 125 | 15 | 1875
14 | Project Administrator | EML | Man-Day | 70 | 30 | 2100
17 | Proposal Management & Coordination | EML | Lump Sum |  |  | 4500
| Subtotal — Abatis (120 man-days + lump sums) |  |  |  |  | 89100
| Subtotal — EML (145 man-days + lump sums) |  |  |  |  | 25750

## Financial Summary
Section | Item | Amount (USD)
A | Professional Services — Abatis | 89100
B | Local Professional Services — EML | 25750
D | Workshops & Capacity Building (4 workshops + materials) | 16000
E | Travel & Logistics (2 intl trips, 20 hotel nights, per diem, local transport, site logistics) | 16500
F | Administrative & Reimbursable Expenses | 7000
G | Technical Contingency & Corporate Overheads | 8000
| Base Cost | 162350
| Profit @ 15% | 30440.63
| Total (excl. taxes) | 192790.63
| VAT @ 18% | 34702.31
| SSCL @ 2.5% | 5687.32
| GRAND TOTAL (USD, incl. VAT + SSCL) | 233180.26
Notes
1. Mirrors Budget_cyber_security.xlsx (agreed internal pricing, 29 Jul 2026).
2. Original internal sizing was ~USD 350k; EML flagged price sensitivity — current pricing reflects competitive positioning with 80/20 technical/price evaluation.
3. Confirm with EML: whether financial proposal must be in USD or LKR; tax treatment of the foreign JV partner (VAT/SSCL applicability to offshore services).
4. Value split ≈ 69% Abatis / 31% EML of professional fees — consistent with agreed ~70/30 allocation.

## Key Personnel
Role in Assignment | Nominee | Party | Credentials / Experience highlights | CV Status
Team Leader | Glyn Richards | Abatis | Career predates DOS; ex-Heathrow Airport — instituted cyber assurance for every initiated project; author of a cyber maturity model still in use 10+ years later; Full Member IISP; leads risk assessment, threat analysis, CMMI/maturity scoring and recommendations | CV NEEDED
Senior OT/ICS Cybersecurity Specialist | (Abatis senior OT/ICS practitioner — confirm nominee) | Abatis | OT/ICS/SCADA security assessment; Gulf smart-city & CNI OT programmes (e.g. Jeddah Central OT cybersecurity, Riyadh Metro OT) | CV NEEDED
Cybersecurity Governance Specialist | Debbie Richards | Abatis | Full Member IISP; governance, policy & compliance frameworks | CV NEEDED
IEC 62443 / C2M2 Specialist | (Abatis — confirm nominee; option: William — 1st class Mathematics (Cambridge), MA Cyber Security (Royal Holloway)) | Abatis | Standards mapping; C2M2 scoring; academically credentialed if TOR requires | CV NEEDED
Training & Capacity Building Specialist | (Abatis/EML joint — confirm) | Abatis | Knowledge transfer, auditor enablement; option: Alex Shipp (academically qualified) | CV NEEDED
Deputy Project Manager / Power Systems & SCADA Engineer | EML selected candidate (confirmed available per CEO, 27 Jul) | EML | Power systems & SCADA engineering; local utility experience; degree-qualified | EML to provide
Local Electrical Engineer | EML nominee | EML | Electrical engineering; site assessment support | EML to provide
Stakeholder Engagement Specialist | EML nominee | EML | PUCSL/utility stakeholder coordination; workshops | EML to provide
QA/QC Manager | EML nominee | EML | Quality management under ISO 9001:2015-certified system | EML to provide
Oversight — CTO | Christian Rogan | Abatis | Abatis CTO; EU cyber-sovereignty & legislative expertise | Optional
Oversight — CCO / Commercial | Chris Barter | Platinum | Full Member, Chartered Institute of Information Security (MCIIS); commercial lead | Optional

## Q&A Answers
# | Question (typical tender/qualification) | Answer
1 | Who is the bidding entity? | Joint Venture of Platinum High Integrity Technologies Limited (Malta) — Lead JV Partner — and EML Consultants PLC (Sri Lanka) — Local JV Partner. Abatis Security Innovations & Technologies GmbH (Switzerland) provides the specialist cybersecurity capability within the Platinum group.
2 | Why is Platinum Malta the lead? | It owns responsibility for the Abatis product, software, IP and international commercial delivery; the lead partner carries the principal technical scope and ~70% commercial allocation (agreed with EML 27–28 Jul 2026). EU-domiciled entity.
3 | Local partner legal status? | EML Consultants PLC, Reg. No. PQ 00240481; incorporated 1993 (originally with Ernst & Young and DHV Netherlands); fully Sri Lankan-owned since 2003; listed on the Colombo Stock Exchange since 2021/22 — the only consultancy company listed on the CSE.
4 | Local partner quality systems? | ISO 9001:2015 (Cert. GISL-0009-QC) and ISO 14001:2015 (Cert. GISL-0009-EC), valid to Feb 2028 (surveillance to Feb 2026 window shown on certificate); 600+ consultancy projects delivered; auditor Lakshman Rupasinghe & Co.
5 | Technical partner track record? | Abatis: Swiss company incorporated Oct 2004; first client was the Swiss government — technology designed at the request of the Swiss government and implemented by the Swiss military for CNI protection. In 20+ years: zero reported breaches against the code and zero CVEs registered — both believed unique in the industry.
6 | What differentiates the technical approach? | Deterministic, rule-enforcing protection that stops attacks in nanoseconds (vs industry mean time to identify/contain of ~270 days, avg cost USD 4.5M per IBM); consultancy & advisory practice of comparable scale to licensing; extensive CNI, smart-city (Gulf), energy and government experience.
7 | JV experience with international firms? | EML: JV with Niras (Netherlands) on Sri Lanka port projects (minor JV partner); multiple collaborations with international firms across 600+ projects. Abatis/Platinum: consortium work across Gulf smart-city programmes, Nigeria (NNPC pilot), Qatar Energy, Latin America deployments.
8 | Relevant sector experience — energy/utilities? | Abatis: OT/ICS security for critical generation and grid-connected infrastructure clients incl. Gulf smart-city utility systems and energy majors (Qatar Energy engagement in progress); EML: power-sector adjacent engineering (electrical, SCADA engineering resources) plus national-level infrastructure consultancy.
9 | Methodology summary? | Information gathering → multi-level structured interviews (verifying processes are actually understood and followed, not just documented) → site/field validation → C2M2 maturity scoring across 10 domains → threat/risk assessment (MITRE ATT&CK for ICS) → standards benchmark (IEC 62443, NIST CSF, ISO 27019) → PUCSL-specific audit framework → workshops & knowledge transfer.
10 | Can you meet the deadline? | Yes — confirmed to EML in writing (27 Jul 2026): resources re-prioritised; proposal preparation under way; WhatsApp coordination group established; EML purchasing official tender pack.
11 | Quality assurance for this assignment? | Dual QA: Abatis technical peer review of all specialist deliverables; EML QA/QC Manager operating under ISO 9001:2015-certified procedures; neither party amends the other's contribution without agreement.
12 | Data protection / security of client information? | Secure artefact-collection portal provided by Abatis for evidence exchange; all assessment data handled under strict confidentiality; deliverables and evidence remain in-country where required by PUCSL; forward-compatible with emerging Sri Lankan data/cyber legislation.

## Outstanding Items
# | Item | Needed From | Why / Blocking
1 | Official tender document pack (purchased from PUCSL) | EML / Jeewaka | Master requirement list — this workbook's response matrix must be verified against it clause-by-clause
2 | Confirmation whether additional forms exist (compliance spreadsheet / Excel annexes) | EML | Glyn's question from 27 Jul call: 'is there any other documentation other than the RFP that needs to be completed, e.g. in Excel?'
3 | Exact submission deadline time, place & number of copies (hard/soft) | EML | Deadline believed Thu 30 Jul; submission is physical in Sri Lanka via EML
4 | Bid security requirement (amount, form, validity) | EML / tender doc | Unknown — could be a hard blocker if bank guarantee needed
5 | Signed JV Letter of Intent (Platinum Malta lead) | Platinum + EML | EML drafting; must reflect Platinum High Integrity Technologies Limited (Malta) as Lead JV Partner per 28 Jul email
6 | Abatis/Platinum corporate documents (incorporation certificates, profile, financials?) | Alexander / Platinum | To mirror EML statutory set; confirm whether both JV partners' financials required
7 | CVs — Abatis key experts (signed, tender format) | Glyn / Debbie / Alexander | TECH-6 equivalent; academic-credential question resolved by fielding Alex Shipp / William if needed
8 | CVs — EML experts incl. selected SCADA/Power Systems engineer | EML | EML confirmed candidate exists; CV not yet received
9 | Number of generation facilities & substations in scope | EML / tender doc | Determines site-visit programme; budget assumes 2 intl missions / 20 site-days
10 | Currency & tax treatment of financial proposal (USD vs LKR; VAT/SSCL on offshore services) | EML | Financial forms cannot be finalised without this
11 | PUCSL existing regulatory instruments & any current cyber provisions | EML | Input to audit framework localisation (Christian's request for local CNI law status)
12 | Reference letters / completion certificates for cited projects (if required) | Both | Typical technical scoring evidence