Proposal: Assessment on Cybersecurity Readiness & Audit Framework Development for Sri Lanka’s Electricity Network

# Security Risk Assessment (SRA)

| Version: | 0.5 |
| --- | --- |
| Date: | 29th July 2026 |
| Author: | Glyn Richards |

Important Confidentiality Notice

The information and data in this document constitute confidential information of Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC are provided for evaluation purposes only to the Public Utilities Commission of Sri Lanka (PUCSL). In consideration of receipt of this document, the recipient agrees to maintain such information in confidence and not to reproduce or otherwise disclose it to anyone outside the individual(s) or entity directly responsible for evaluating its contents. These confidentiality restrictions shall not apply to any such information known to the recipient without restriction before receipt of this document as evidenced by written business records, which become publicly known through no fault of the recipient or rightfully received by the recipient from a third party without restriction.

This document includes information about current Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  products, sales, and service programs that may be enhanced or discontinued at Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC 's sole discretion. Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  has endeavoured to include in this document the materials that are believed to be reliable and relevant for the recipient's evaluation. Neither Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  nor its representatives make any warranties as to the accuracy or completeness of the information. Accordingly, this document is provided for information purposes only and for you to assess as appropriate to your business needs. Neither Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  nor its representatives shall have any liability to the recipient or any of its representatives due to the use of the information provided.

This report does not constitute an offer capable of your acceptance and is subject to the agreement of a formal contract specifying terms and conditions. No contractual relationship shall arise until both parties have signed a formal contract. Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  consultants will not commence work under this proposal without a formal written agreement signed by both parties.

The term “solution” in the context of this document is defined as the products and services proposed herein. Since additional information may be required from the Public Utilities Commission of Sri Lanka to develop the appropriate configuration for a specific project, the term “solution” does not imply that those products or services as proposed are guaranteed to, or will, meet any mandated or implied requirements or integrate or inter-operate with any other products, processes or systems.

Unless otherwise agreed in writing, pricing estimates and proposal terms are valid for 60 calendar days from the closing date of the proposal submission as per RFP stipulations.

Sri Lanka Right to Information Act 2016 Statement of Confidential Commercial Information

All information in this proposal is provided in confidence. In addition to the confidentiality of the information, the content of this proposal is commercially sensitive. Any disclosure of this proposal would significantly harm the competitive position of Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  because the company has invested considerable time, effort and know-how into the project, aiming to differentiate itself from its competitors. The solution put forward to you contains many aspects unique to Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  (including, but not limited to, end-user information, Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  proprietary trade secrets, pricing and discount data) and consequently is exempt from disclosure under the Right to Information Act, No. 12 of 2016 (under Section 5(d)).

© Copyright 2026 Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC.

Contents

1	Overview	5

2	Objectives	5

3	JV and Contracting Structure	6

4	Business & Organisational Overview	6

5	In-Scope	6

6	Exclusions	7

7	SRA Project	8

8	Phase Action Items & Key Tasks	9

9	Costs Table	10

10	The Security Risk Assessment	11

11	Reference Documents	11

12	Key Project Outputs & Expected Outcomes	12

13	Indicative Terms of Reference	12

Overview

Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC is pleased to present this proposal to the Public Utilities Commission of Sri Lanka (PUCSL) for the Assessment on Cybersecurity Readiness of Electricity Network and Critical Generation Facilities in Sri Lanka & Development of a Cybersecurity Audit Framework specific to grid operations, SCADA, and critical infrastructure protection.

Sri Lanka’s national transmission grid and power generation infrastructure depend on tightly integrated Operational Technology (OT) and Information Technology (IT) systems. Key components include Supervisory Control and Data Acquisition (SCADA), Energy Management Systems (EMS), substation automation, and specialized industrial communication protocols (e.g., DNP3, IEC 61850). Ensuring the cybersecurity resilience and regulatory compliance of these critical assets is vital for national energy security, public safety, and operational reliability.

Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC brings extensive global expertise in OT/ICS cybersecurity, grid protection, and international framework alignment (C2M2 v2.1, IEC 62443, ISO/IEC 27001, NIST CSF, ISO 31000). In line with the execution schedule, our specialised consulting team will conduct a non-intrusive maturity assessment, establish a quantitative security baseline and cost-aware remediation roadmap, craft a Sri Lanka-specific Cybersecurity Audit Framework for grid operations, and deliver comprehensive capacity building and operational toolkits to ensure self-sustained resilience.

Objectives

The primary objectives of this engagement are structured to deliver clear, actionable, and sustainable cybersecurity governance across Sri Lanka's electricity sector:

- Task 1: Cybersecurity Maturity Assessment & Gap Analysis: Evaluate current cyber maturity across all 10 C2M2 v2.1 domains, analyse macro-level technical risks within grid operations (SCADA/EMS, network protocols), and benchmark findings against international standards (ISO/IEC 27001, IEC 62443, NIST CSF).

- Task 2: Establishment of Maturity Baseline & Remediation Roadmap: Create a quantitative "Point Zero" Maturity Profile (MIL scores), compile a defensible Evidence Ledger, and formulate a prioritized, cost-aware Remediation Roadmap to close identified security gaps.

- Task 3: Cybersecurity Governance Framework Development: Define target MILs across asset classes, author a tailored Compliance Framework and Audit & Verification System (with RACI matrices and standardized audit checklists), and establish a benchmarking methodology with defined KPIs.

- Task 4: Institutional Capacity Building & Operational Readiness: Equip the National System Operator (NSO), Transmission Network Operator, and PUCSL with practical operational toolkits (risk registers, incident response templates, monitoring dashboards), Standard Operating Procedures (SOPs), regulatory compliance guides, and hands-on workshops for technical and executive leadership.

JV and Contracting Structure

Proposed formal structure: Platinum High Integrity Technologies Limited, Malta, as Lead Joint Venture Partner, with EML Consultants PLC as Local Joint Venture Partner.

Lead Partner: Platinum High Integrity Technologies Limited (Malta)

Local Partner: EML Consultants PLC

Joint Venture Identifier: "Platinum–EML JV" (or "the Consortium")

| Area | Platinum Malta | EML Consultants PLC | Joint control |
| --- | --- | --- | --- |
| JV leadership | Lead partner and principal contracting entity | Local JV partner | Governed by the signed JV agreement |
| Technical proposal | Lead methodology, staffing strategy, technical work plan and principal technical deliverables | Provide local technical input, utility-sector context and local engineering support | Final approval by both parties |
| Project delivery | Lead specialist OT/ICS, SCADA, governance, maturity and audit-framework work | Lead local coordination, stakeholder engagement, workshops, logistics and implementation support | Integrated project management and reporting |
| Proposal submission | Approve final technical and financial submission | Coordinate local preparation and physical submission | No substantive amendment without mutual approval |
| Client communications | Copied on all procurement correspondence | Copied on all procurement correspondence | Joint approval of substantive responses |
| Commercial basis | Approximately 70%, subject to final resource loading | Approximately 30%, potentially adjusted for confirmed local workload | Final allocation agreed after staffing and pricing are completed |

Business & Organisational Overview

The Public Utilities Commission of Sri Lanka (PUCSL) serves as the statutory regulator of the electricity industry in Sri Lanka, overseeing the generation, transmission, distribution, supply, trade, and procurement of electricity across the island.

As Sri Lanka’s electricity sector increasingly relies on digitally interconnected platforms (SCADA, EMS, Substation Automation, WAN/LAN data links), the potential impact of cyber threats grows. Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC ’s consultancy engagement is structured to support PUCSL’s regulatory mandate by delivering a robust oversight mechanism, raising sector-wide capability maturity, and aligning national critical infrastructure protection with international energy sector practices.

Consultant's Organisation & Experience

Lead JV Partner — Platinum High Integrity Technologies Limited (Malta), with Abatis Security Innovations & Technologies GmbH (Switzerland)

Abatis Security Innovations & Technologies GmbH was incorporated in Switzerland in October 2004. Its founding engagement was at the request of the Swiss government: technology designed for national critical-infrastructure protection and implemented by the Swiss military. Over 20+ years of operation there has been no reported breach against the Abatis code and no publicly registered security vulnerability recorded against it — a record we believe is unique in the security industry.

- Deterministic, rule-enforcing protective technology: attacks are stopped before they start, in nanoseconds — against an industry mean time to identify and contain a breach of ~270 days at an average cost of USD 4.5M (IBM, global).

- Portfolio spans critical national infrastructure, smart-city OT programmes in the Gulf, energy-sector engagements (including a current engagement with a Gulf national energy company), government projects in Africa and Latin America, and OEM security integration at device-manufacturing point.

- Consultancy and advisory (governance, risk, maturity assessment, regulatory support) represents a substantial share of the group's business alongside technology licensing.

- Platinum High Integrity Technologies Limited (Malta) is the group's EU-domiciled entity, owns the commercial delivery of the Abatis capability, and leads the Joint Venture. UK affiliate: Platinum High Integrity Technologies Limited, Kemp House, 152–160 City Road, London EC1V 2NX (Company No. 13674653).

Local JV Partner — EML Consultants PLC (Sri Lanka)

EML Consultants PLC is Sri Lanka's only consultancy company listed on the Colombo Stock Exchange, with over 600 consultancy projects delivered across engineering, environment, water, irrigation, urban infrastructure, governance and capacity building.

- Incorporated 1993 as EML Consultants (Pvt) Ltd — originally established with Ernst & Young and DHV Netherlands; fully Sri Lankan-owned since 2003; re-registered as EML Consultants PLC (Reg. No. PQ 00240481), listed on the CSE (effective 19 November 2021).

- ISO 9001:2015 (Certificate GISL-0009-QC) and ISO 14001:2015 (Certificate GISL-0009-EC) certified; registered member of the Central Environmental Authority; member of the National Chamber of Commerce.

- International JV experience including with Niras (Netherlands) on Sri Lanka port projects; current major assignments include a hyperscale data-centre project, a 50-storey mixed development at Port City Colombo and the Grand Hyatt Colombo project.

Corporate Information (TECH-2 Section A)

| Field | Platinum High Integrity Technologies Ltd (Malta) | EML Consultants PLC |
| --- | --- | --- |
| Business Registration | [TBC — Malta incorporation certificate] | PQ 00240481 (ROC & Colombo Stock Exchange) |
| Date of incorporation | [TBC] | 1993 (PLC listing effective 19 Nov 2021) |
| Registered address | [TBC — Malta]; UK affiliate: Kemp House, 152–160 City Road, London EC1V 2NX | No. 6/10, Rajamaha Vihara Mawatha, Pitakotte, Sri Lanka |
| Email / Telephone | [TBC] | info@emlconsultants.com / +94 11 553 5880 |
| Website | www.abatis.ch | www.emlconsultants.com |
| Annual turnover — last 3 years (audited) | [TBC — confirm whether required of Lead Partner] | [Insert audited figures — must evidence ≥ Rs. 60 million per year] |

Similar Assignments (TECH-2 Section B)

Reference assignments to be presented in the prescribed format (client, contract value, duration, staff months, services). Key references include: [complete values before submission]

| Assignment | Client | Value | Duration | Staff-months | Services |
| --- | --- | --- | --- | --- | --- |
| OT cybersecurity — smart-city infrastructure programme (Gulf) | [TBC] | [TBC] | [TBC] | [TBC] | OT/ICS security design & assurance |
| National CNI protection deployment (Switzerland) | Swiss Government / Military | [TBC] | 2004 onwards | [TBC] | CNI protective technology & advisory |
| Energy-sector security engagement (Gulf national energy company) | [TBC] | [TBC] | [TBC] | [TBC] | OT security assessment & demonstration |
| National petroleum company cybersecurity pilot (Nigeria) | NNPC | [TBC] | [TBC] | [TBC] | CNI cybersecurity pilot |
| Port development projects (Sri Lanka) — JV with Niras (NL) | [TBC] | [TBC] | [TBC] | [TBC] | Engineering consultancy (EML, JV partner) |

In-Scope

In-Scope Infrastructure & Locations

The scope encompasses macro-level architectural, procedural, and governance assessments across critical operational and generation infrastructure in Sri Lanka, including:

- National System Control Centre (NSCC)

- Lakvijaya Power Station (Thermal Generation)

- Victoria Power Station (Hydro Generation)

- Kotmale Power Station (Hydro Generation)

- Biyagama Grid Substation

- Selected Telecommunication & Data Network Hubs supporting power grid communications

- IT/OT Data Interfaces & Protocol Flows between the National System Operator (NSO), National Transmission Network Service Provider, and grid-connected generation plants.

Site Visit & Field Assessment Programme

Non-intrusive site assessments are conducted at the in-scope facilities (NSCC, Lakvijaya, Victoria, Kotmale, Biyagama and selected communication hubs) by Abatis OT/ICS specialists working alongside EML's power-systems and SCADA engineers. Site activities comprise structured walk-downs, read-only architecture and configuration reviews, physical/environmental control observation and on-site interviews — all under site safety protocols and with prior written approval from PUCSL and the system operators. The programme provides for approximately 20 site-days across two international missions, supported continuously by the EML local engineering team.

Exclusions

Explicit Exclusions & Non-Disruption Guarantees

- No Active/Intrusive Vulnerability Assessment or Penetration Testing (VAPT): To guarantee zero operational disruption to live generation and transmission systems, this assessment is strictly limited to capability maturity (C2M2), architectural analysis, configuration reviews, and policy auditing. Active "white hat" exploits, invasive network scanning, or live system stress testing are explicitly excluded.

- No Direct Deployment of Security Controls: Implementation of physical or technical controls, live environment reconfigurations, or hardware modifications are excluded from this advisory phase.

- Safety & Operational Safety Assurance: All assessment activities will be conducted in strict compliance with site protocols and prior written approval from PUCSL and system operators.

SRA Project

Project Timeframe Summary

| Cyber Security Risk Assessment Process Phases |  |  |
| --- | --- | --- |
| Phase | Activity | Duration in Days |
| Phase 1 - Planning | Schedule a planning session to prepare for the upcoming analysis period thoroughly. Collaborate with the client to establish the focus areas, goals, and desired outcomes during this session. This will help align everyone's expectations and set the stage for a successful analysis period. | 5 |
|  | Prepare a detailed scope document outlining the specific areas of assessment and the scope of work to be performed in collaboration with the client. This document clearly defines the objectives, deliverables, timelines, and relevant details related to the assessment process. | 1 |
| Phase 2 - Information Gathering. | Gather all pertinent documents, including the security document set, policies, processes, procedures, high-level architecture, and system operating procedures. | 5 |
| Phase 3 - Conduct the Risk Assessment. | Review the documentation that has been provided and make necessary updates to the Risk Profile. It is estimated that each document will take half a day. | 30 |
|  | Conduct interviews with relevant personnel, such as operators, system developers, network administrators, information owners, and security officers. Each interview is estimated to take a day. Update the Risk Profile accordingly. Estimated 10 People | 8 |
| Phase 4 - Deliver Final Assessment Report. | Prepare a detailed draft of the risk assessment report, including identified risks, their potential impacts, and suggested recommendations and mitigation strategies. | 10 |
|  | Conducted an internal review of the draft report, carefully examining content, accuracy, formatting, and compliance with company standards and procedures. | 1 |
|  | Prepare and finalise the report, including all necessary details and findings, and send it to the client for review and consideration. | 1 |
|  | Prepare for and conduct a comprehensive meeting with the client to review the findings of the risk assessment in detail. Discuss the potential risks, their implications, and proposed mitigation strategies. Obtain the client's approval and sign off on the report to ensure alignment with their expectations. Subsequently, the final, detailed report will be issued incorporating all the points discussed and the approved findings. | 2 |
|  | Total Number of Days (Dependent on availability of resources) | 63 |

Phase Action Items & Key Tasks

| Phase | Actions |
| --- | --- |
| Phase 1 - Planning | Planning Meetings to prepare for the analysis period, focus areas, goals, and desired outcomes. Prepare a portal guide and give access to the portal share. Providing support to Staff regarding the Portal. Agree on the scope of assessment with the client. |
| Phase 2 - Information Gathering. | Create the Evidential Document Request List. Create Risk Assessment Profile. |
| Phase 3 - Conduct the Risk Assessment. | Review the documentation provided (half a day per document). |
|  | Conduct interviews with related personnel such as operators, system developers, network administrators, information owners, and security officers. (Half a day per interview) Estimated 10 People |
| Phase 4 - Final Assessment Report. | Analysis & prepare draft report. |
|  | Complete Internal document review process. |
|  | Final Report sent to the client. |
|  | Meeting with the client to discuss findings. |

Costs Table

[Internal note — do not print in Technical Proposal: this tender uses two separately sealed envelopes. All pricing in this section must be removed from the Technical Proposal and submitted only within the Financial Proposal forms FIN-1 to FIN-5. Reconcile the fee basis with the master response workbook (resource-loaded USD 354,605.55 incl. profit and SSCL) before finalising FIN-3 per-expert rates.]

Costs to provide the risk assessment as detailed in the Project Plan and Delivery Table:

Daily Team Cost: $5,500 / day (5 personnel @ $1,100/day per resource)

Total Effort: 315 Person-Days

Total Fee: $346,500

| Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC Service | Cost Per Day |  |  |
| --- | --- | --- | --- |
| Cyber Security Risk Assessment (N people for N days on project, N days preparation and reporting) | $ 5500 |  |  |
| Phase | Days | Percentage | Cost USD |
| Phase 1: Planning | 6 | 9.52% | $ 33000 |
| Phase 2: Information Gathering | 5 | 7.94% | $ 27500 |
| Phase 3: A Review of Documentation | 30 | 47.62% | $ 165000 |
| B Interviews | 8 | 12.7% | $ 44000 |
| Phase 4: Final Assessment Report | 14 | 22.22% | $ 77000 |
| TOTAL | 63 | X $5,500/Day | $ 346500 |
| Maximum Expenses |  |  |  |
| Note : - schedule assumed 5 people working concurrently over 63 calendar days, the total workload is 315 person-days (63 days×5 people). |  |  |  |

Payment is to be completed after each phase and sub phase is completed, equalling to 5 payments in total.

Any expenses that occur will be pre-authorised with the Client @cost + 20%

Note: Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  prices will be held for 90 days.

Expenses for on-site work will not exceed the abovementioned amount and will be charged on project completion.

Timelines

Detailed project schedules will be discussed and mutually agreed upon upon contract award.

Project Management

It is envisaged that the tasks associated with the project will include,

- Participate as a member of the PUCSL project team (roles to be determined);

- Provide weekly exception reports and other reports as requested throughout the project timeframe.

- Achieve Practical Completion within the allocated time frame and budget.

Please note that specific task responsibilities will be confirmed as part of the scope definition during phase 1:Planning

Project Liaison

The project will be delivered cooperatively between PUCSL and the PHIT consultant.

All enquiries and correspondence should be directed to the Project Manager for this project, with email being the preferred method: <<TBA>>

Conduct of the Project

The PHIT consultant to work during regular PUCSL business hours.

The Platinum High Integrity Technologies Limited (Malta) (PHIT) and EML Consultants PLC  is expected to provide a team of subject matter experts, at least one of which will be dedicated 100% to the tasks, documenting and writing the SRA and findings, etc, which will be the PHIT consultant's primary responsibility.

Tasks may include, but are not limited to,

Review and analysis of provided client documentation, including Threat Assessments, Security Reviews, Incident Reports, Security Instructions, network and SCADA/EMS architecture documentation, etc.

Interviews with PUCSL managers and staff.

Consultation with internal and external stakeholders.

The Security Risk Assessment

The core maturity model will utilize DOE C2M2 v2.1, with risk assessment methodology executed according to ISO 31000:2018 and cross-referenced against the Secure Controls Framework (SCF).

The SRA methodology will use the Secure Controls Framework Cyber Security and Data Privacy Risk model, be compliant with ISO31000:2018 Risk Management Standard, and identify and address other relevant guidelines/standards.

The SRA will address the organisation's collective operations, considering differing conditions and business environments across the network to minimise the possibility of harm to staff, visitors, assets, and information in all situations and anticipated events. Regional and local input is critical to any threat assessment to ensure accurate risk ratings are ascertained.

There will be a conscious effort to maximise the transparency of the SRA methodology to ensure that the functionality of PUCSL  operations is maintained at an optimum. Notwithstanding this, it is also recognised that security and safety be maintained at a level that will identify and comply with relevant standards and operational requirements.

Cybersecurity Audit Framework Development

The second core deliverable of the Terms of Reference is a PUCSL-specific Cybersecurity Audit Framework enabling the regulator to audit licensees' cybersecurity on a repeatable, defensible basis. The framework comprises:

- Audit universe & scoping model — which entities, systems and facilities are auditable, with criticality-based tiering (grid operations, SCADA/EMS, generation control, market systems).

- Control catalogue — mapped to C2M2 domains, IEC 62443 and NIST CSF, tailored to Sri Lankan grid operations.

- Audit procedures & evidence requirements per control — what an auditor asks, observes, tests and collects.

- Maturity-based scoring & reporting templates — consistent scoring, findings classification and board/regulator-level reporting formats.

- Audit cycle & escalation model — frequency by criticality tier, follow-up and remediation tracking, regulatory escalation.

- Auditor competency requirements — skills, training and certification expectations for PUCSL audit staff.

- RACI matrices and standardised audit checklists for every audit procedure, with target maturity indicator levels (MILs) defined per asset class.

- Benchmarking methodology with defined KPIs, enabling PUCSL to track sector-wide capability maturity over successive audit cycles.

Local SOPs and regulatory guidance notes are co-developed with EML, drafted to operate under current Sri Lankan law while remaining forward-compatible with anticipated national cyber/CNI legislation.

Capacity Building & Knowledge Transfer

Four workshops are delivered (local delivery by EML, content by Abatis), with all training materials handed over for PUCSL's continued use. Alongside the workshops we deliver practical operational toolkits to the NSO, the Transmission Network Operator and PUCSL: risk registers, incident-response templates, monitoring dashboards, SOPs and regulatory compliance guides.

| Workshop | Purpose |
| --- | --- |
| Project Kick-off Workshop | Scope, expectations, data-collection mobilisation. |
| Technical Findings & Governance Framework Workshop | Validation of assessment findings and draft framework with stakeholders. |
| Knowledge Transfer Workshop | Auditor enablement: operating the audit framework, C2M2 re-assessment, continuous monitoring; train-the-trainer materials. |
| Executive Presentation & Final Workshop | Leadership briefing on findings, roadmap and framework adoption. |

Team Composition & Responsibility Matrix

The Joint Venture fields the following team (TECH-5 detail and signed CVs per expert to follow; one CV per position):

| Role | Party | Man-Days | Key Responsibilities |
| --- | --- | --- | --- |
| Team Leader | Abatis | 60 | Technical direction; risk assessment; maturity scoring; recommendations |
| Senior OT/ICS Cybersecurity Specialist | Abatis | 60 | SCADA/EMS/DCS assessment; threat analysis; site assessments |
| Cybersecurity Governance Specialist | Abatis | 40 | Governance & compliance framework; policy review |
| IEC 62443 / C2M2 Specialist | Abatis | 20 | Standards mapping; C2M2 scoring; audit framework controls |
| Training & Capacity Building Specialist | Abatis | 20 | Workshops content; toolkits; knowledge transfer |
| Power Systems / SCADA Engineer (Deputy PM) | EML | 100 | Local project management; SCADA engineering; site programmes |
| Local Electrical Engineer | EML | 50 | Electrical engineering; field assessment support |
| Stakeholder Engagement Specialist | EML | 15 | PUCSL/utility coordination; workshop logistics |
| QA/QC Manager | EML | 10 | Quality assurance under ISO 9001:2015-certified system |
| Technical Report Coordinator | EML | 15 | Deliverable production & document control |
| Project Administrator | EML | 30 | Administration, logistics, correspondence |

Professional credentials include Full Membership of the Chartered Institute of Information Security (MCIIS) and full membership of the IISP; academically credentialed specialists (including first-class Mathematics, Cambridge; MA Cyber Security, Royal Holloway) are fielded where the evaluation requires. [Named experts and signed CVs — TBC]

Quality Assurance & Information Security

- Governance: the Abatis Team Leader directs the technical programme; the EML Deputy Project Manager manages local delivery; joint weekly progress reviews; both parties copied on all PUCSL correspondence.

- Dual QA: Abatis technical peer review of every specialist deliverable; EML QA/QC Manager operating under its ISO 9001:2015-certified system; neither party amends the other's contribution without prior agreement.

- Information security: secure artefact-collection portal for all assessment evidence; strict confidentiality handling; in-country retention of sensitive material where required by PUCSL.

Comments on the Terms of Reference (TECH-3)

- Secure document exchange: we recommend, and will provide, a secured artefact-collection portal for assessment evidence for the duration of the engagement.

- Scope confirmation: we request confirmation of the final list of generation facilities and substations in scope to firm up the site-visit programme.

- Counterpart facilities: we request PUCSL nominate counterpart staff, provide access to relevant documentation and facilitate site access approvals with system operators.

- Legislative context: the audit framework will operate under current Sri Lankan law while remaining forward-compatible with anticipated CNI legislation; the JV can support subsequent legislative drafting as follow-on advisory.

Reference Documents

Throughout the project, the Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC-HIT consultant is expected to obtain all relevant documents, information, and reports required to conduct it and prepare and justify the final outputs with high professionalism and certified quality.

Any relevant PUCSL documents may be loaned to the successful Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC-HIT consultant on a confidential basis.

PUCSL documents must not be copied and must be returned upon completing the Brief.

Key Project Outputs & Expected Outcomes

Outcomes of the consultancy project will include:

- Inception Report — confirmed scope, stakeholder map, data-request register and detailed schedule.

- Cybersecurity Readiness Assessment Report — C2M2 v2.1 maturity profile ('Point Zero' baseline, MIL scores per domain), Evidence Ledger, threat & risk assessment and prioritised, cost-aware remediation roadmap.

- Cybersecurity Audit Framework — control catalogue, audit procedures, RACI matrices, scoring and reporting templates, audit cycle and auditor competency requirements, ready for PUCSL adoption.

- Standard Operating Procedures (SOPs) and regulatory guidance notes localised for Sri Lankan utilities.

- Training materials, workshop reports and operational toolkits (risk registers, incident-response templates, monitoring dashboards) for the NSO, Transmission Network Operator and PUCSL.

- Final Report and Executive Presentation, including framework adoption plan and follow-on roadmap.

Indicative Terms of Reference

The report and methodology will include all documentation relevant to the SRA and, in particular, will identify, examine and document the following:

- Assets at risk, sources of risk, and the how, when, where and why incidents may occur, including the surrounding circumstances.

- Provide a detailed list of vulnerabilities and threats, including whether any weakness in the system or method of control is likely to cause or contribute to an incident.

- Remedial or other action is necessary to ensure adequate security risk management, including modifying operating instructions, systems, procedures, training, infrastructure, or equipment and identifying indicative budgets and responsible actioners.

- Reference relevant standards, legislation, and PUCSL specific operational requirements and identify mandatory standards.

- Related issues such as natural disasters, physical resilience and safety interfaces within the context of cybersecurity risk management.

Annex — Submission Compliance Checklist

| Form | Requirement | Status |
| --- | --- | --- |
| TECH-1 | Technical Proposal Submission Form, signed by authorised signatory | Drafted — signature & PoA required |
| TECH-2 | Organisation & experience incl. BR certificates, turnover ≥ Rs. 60M/yr audited | Partially complete — turnover figures & Malta documents outstanding |
| TECH-3 | Comments on TOR (optional) | Included in this document |
| TECH-4 | Methodology: approach, C2M2, IEC 62443, NIST CSF, governance & audit framework, work plan, organisation | Included in this document |
| TECH-5 | Team composition & task assignments | Included — named experts to be confirmed |
| TECH-6 | Signed CVs, one per position | Outstanding |
| TECH-7 | Staffing schedule bar chart (office/field, local/foreign, staff-months) | To be produced from Team Composition table |
| TECH-8 | Work schedule Gantt with deliverables & milestones | Per Project Timeframe Summary — to be formatted |
| FIN-1 to FIN-5 | Financial forms incl. per-expert remuneration and breakdown of cost by activity | Separate sealed envelope — see internal note at Costs Table |
| Packaging | 1 original + 2 copies technical, 1 original financial, USB soft copy, two sealed envelopes in one outer | Noted for submission |

SIGNED for and on behalf of Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC  by:

<<Name and Title of person signing for Platinum High Integrity Technologies Limited (Malta) and EML Consultants PLC >>

__________________________________________________
Authorised Signature

Date: ____________

SIGNED for and on behalf of the Client by:

<<Name and Title of person signing for the Client>>

__________________________________________________
Authorised Signature

Date: ____________